## Mentor meeting
No. | Date | Time | Who | Where | What | Mentor
1 | 2018-10-05 | 9:00 | Team, Mentor and one member from the company | Narrow Pacific Company | Mr. Vu introduce about his company platform Share and disucss idea for Capston | Yes
2 | 2018-10-06 | 19:00 | Team, Mentor | Linda coffee shop | Diccuss about features and core value of the project | No
3 | 2018-11-01 | 15:00 | Team, Mentor | Room 1101, Nguyen Van Linh | Review progress of the project | Yes
4 | 2018-11-17 | 16:00 | Team, Mentor | Room 1101, Nguyen Van Linh | Review progress of the project | Yes

## Team meeting
No. | Date | Time | Who | Where | What | Mentor
1 | 2018-09-29 | 17:00 | Members | Room 1101, Nguyen Van Linh | Choose features for the project
2 | 2018-10-04 | 14:00 | Members | IOT space | Review UI
3 | 2018-10-11 | 14:00 | Members | IOT space | Test smart contract and diccuss around it
4 | 2018-10-18 | 14:00 | Members | IOT space | Find out solutions how to connect ReactJS and Ethereum
5 | 2018-10-29 | 15:00 | Members | IOT space | Review architecture
6 | 2018-11-06 | 14:00 | Members | IOT space | Review database
7 | 2018-11-14 | 14:00 | Members | IOT space | Finding solutions for interacting Browser and Metamask
8 | 2018-11-22 | 14:00 | Members | IOT space | Report Firebase database